## Overview
Component 2 - Real Implementation Plan
Branch-aware plan based on the TAF, the existing Antigravity workbook, and verified code in Component_02_RH as of 2026-09-22.
Verified branch snapshot
Current branch | Component_02_RH | Git relation | 81 commits ahead of origin/Component_02_RH; most are merged team work | Component 2 history | Latest committed Component 2 change: 76c43a3 (deterministic scoring engine) | Working tree | Scoring-engine edit plus untracked boundary-test file
API build | Passed: 0 warnings, 0 errors | Component 2 tests | 44 passed, 0 failed | OCR batch | 73/96 fields correct (76.0%) on 24 synthetic text documents | UI | Placeholder only
TAF capability and implementation gate
Capability | TAF requirement | Current state | Acceptance evidence | Capability | TAF requirement | Current state | Acceptance evidence
Financial documents | Process bank statements, salary slips, optional CRIB reports, and income records | Partial | Versioned benchmark with field-level accuracy, confidence and safe manual-review behavior | A-E feasibility | A/B strong, C moderate, D/E high risk | WIP | Approved rubric, deterministic boundary tests, explanations and escalation behavior
Approval prediction | Estimate lease success probability from financial behavior and historical outcomes | Not started | Held-out ROC-AUC, PR-AUC, Brier score and calibration report | Historical case analysis | Analyze approved and rejected lease cases | Not started | De-identified case schema, corpus provenance and outcome rationale
RAG learning | Retrieve relevant historical cases for case-based learning | Not started | Labeled retrieval test set with Precision@K/Recall@K and cited case IDs | Proposal generation | Generate structured proposals aligned with successful patterns | Not started | Constraint-valid structured output, grounded case references, failure-safe fallback and human review
Immediate execution order
1 | Reconcile the written A-E rubric with the current engine before training any model. |  | Plan status | Count |  | Scope rule | Plan position
2 | Correct input semantics: application ID, requested lease cost, monthly debt, optional CRIB, and evaluation timestamp. |  | Ready | 1 |  | e-Slims | Complement the existing administration workflow; do not claim replacement.
3 | Raise document extraction reliability from the verified 76.0% synthetic baseline and add confidence/manual-review output. |  | Decision needed | 1 |  | Real financial data | Use only after institutional authorization, ethics/privacy clearance and retention controls.
4 | Finish one secure assess-feasibility API vertical slice before ML, RAG, persistence expansion, or UI polish. |  | External gate | 2 |  | Synthetic results | Valid for pipeline research; not evidence of real applicant predictive performance.
5 | Build the approval model and RAG pipeline with explicit synthetic-data limitations and reproducible evaluation. |  | Not started | 36 |  | AI decisions | Decision support only. Manual review and appeal paths remain required.
6 | Add persistence, UI, cross-component events, security gates, and final research evaluation. |  | Total tasks | 40 |  | Policy limits | Source from approved policy/legal material; do not copy unverified constants from another module.

## Current State
Current implementation state
Statuses distinguish committed/verified behavior from scaffolding, uncommitted work, and absent capabilities.
Workstream | Status | What exists | Verified evidence | Gap or concern | Next action
Scope and output contracts | Partial | Scope, feature dictionary, output DTOs, synthetic schema and OCR decision documents | Files exist under docs/ and align broadly with TAF Component 2 | Documents are inconsistent with the actual scoring engine and make unsupported OCR accuracy/cost claims | Update one authoritative research and implementation contract
Domain model | Partial | Enums, assessment and proposal entities, value objects, domain events and engine interfaces | Domain tests are included in the 44 passing tests | FinancialProfile bypasses validation; IncomeProfile duplicates part of it; object-typed engine inputs are not safe contracts | Consolidate validated domain inputs and typed service contracts
Synthetic applicant generator | Partial | Python generator for 1,000 applicant/outcome rows | Generator code is committed | No generated dataset is present; no fixed seed/version; grades are sampled before correlated features, so evaluation may overstate validity | Add deterministic seed, data card, provenance, leakage review and versioned output
Document OCR and extraction | Partial | Azure Document Intelligence client, mock mode, regex field extraction for bank, salary and CRIB documents | 24-document batch: 73/96 fields, 76.0% | Generic prebuilt-document text plus brittle regex; no confidence output; CRIB is mandatory in command despite being optional in TAF | Separate OCR transport and parsers, add confidence/manual review, improve benchmark
PII and document security | Partial | Masked logging payload for applicant/employer identifiers | PiiMasker unit tests pass | No upload type/size validation, malware gate, URI/SSRF control, retention policy, encryption or authorization path | Create threat model and secure ingestion/retention design before real data
Assessment command | Partial | Extracts three documents, builds a profile, calls scoring engine and repository, maps result DTO | Handler unit test passes | Validator is not invoked; income consistency is hard-coded to 0.85; persisted assessment receives ApplicantId as ApplicationId; input timestamp is ignored | Fix contracts, validation, identifiers and deterministic time handling
Deterministic A-E scoring | WIP | Weighted scoring engine with grade mapping and factor breakdown | Committed engine builds; uncommitted 80/60/40/20 boundary tests pass | Written rubric says 85/70/50/30 and different weights; lease cost is proxied by savings; debt is assumed as 5% of total; overdrafts are ignored | Supervisor-approved scoring decision, then implement and lock boundary tests
Approval prediction | Not started | Interface, DTO and handler shell | Handler throws NotImplementedException | No dataset pipeline, model, calibration, metrics or runtime wrapper | Implement only after data contract and split strategy are frozen
Historical case retrieval and RAG | Not started | Repository and optimizer interface placeholders | No corpus, embedding, retrieval service or evaluation artifacts | Interfaces use object; no provenance, citations, prompt safety or relevance metrics | Create typed case schema and evaluated retrieval pipeline
Proposal generation | Not started | LeaseProposal entity and DTO plus handler shell | Handler throws NotImplementedException | No structured LLM output, policy constraints, retry/fallback, grounding or human review | Implement constraint-first generator after retrieval is validated
Persistence | Not started | Repository interfaces only | Infrastructure persistence folder contains placeholder only | No DbContext, migrations, mappings or repositories | Add separate lease_feasibility schema after domain contracts stabilize
API registration and endpoints | Not started | Presentation project exists | API builds but Program.cs has no LeaseFeasibility registration; controller folder is empty | No assess, predict or proposal endpoint; no Swagger group or auth policy | Deliver a secure assess endpoint first, then the other two
Component 2 web UI | Not started | Route and module folders exist | Page displays a coming-soon placeholder | No upload, results, error states, traceability or review workflow | Build UI after stable API contracts
Tests and build | Partial | Domain, handler, OCR and PII unit tests | 44 tests passed; API build passed with 0 warnings and 0 errors | Mostly mock/unit coverage; no database, API, authorization, real OCR, ML, RAG or browser E2E tests | Add tests with each vertical slice and final end-to-end evidence
Data access and ethics | External gate | TAF permits synthetic data when real data is unavailable | No verified institutional data access or ethics approval in the branch | Real banking/CRIB/approval data cannot be assumed | Keep research synthetic/de-identified until written authorization and ethics/privacy clearance

## Implementation Plan
Remaining implementation plan - 40 working days
Run sequentially by gate. Estimates assume one primary developer with Antigravity assistance; external approvals and real-data acquisition are not included in the 40-day engineering estimate.
Seq | Phase | Day | Priority | Task | Deliverable | Acceptance gate | Depends on | Antigravity mode | Status
1 | 0. Baseline and contracts | 1 | Critical | Capture a clean baseline of Component 2 commits, preserve the current dirty scoring work, and record commands/results used for verification. | Branch snapshot and baseline note | Dirty work is preserved; Component 2 tests and API build are repeatable | None | Review-driven | Ready
2 | 0. Baseline and contracts | 2 | Critical | Reconcile the A-E thresholds, weights, penalties and actions between feasibility-rubric.md, the engine and the uncommitted tests. | Scoring decision record and updated rubric | One approved table defines A-E boundaries, weights, C review and D/E escalation | Supervisor/domain decision | Chat first, then review diff | Decision needed
3 | 0. Baseline and contracts | 3 | Critical | Replace proxy/ambiguous inputs with explicit semantics: application ID, applicant ID, requested rent or lease cost, monthly debt obligation, statement period and optional CRIB. | Typed input contracts and feature dictionary | Every scoring input has unit, period, source and validation rule | Task 2 | Review-driven | Not started
4 | 0. Baseline and contracts | 4 | Critical | Define data governance: synthetic-only default, consent/authority, retention, encryption, access roles, redaction and audit metadata. | Data protection and ethics checklist | No real financial document can enter the system without an approved control path | Institutional/ethics guidance | Human-owned decision | External gate
5 | 1. Document intelligence | 5 | High | Split the OCR provider client from document-specific field extraction and normalization. | IOcrTextProvider plus typed extractors | Mock and Azure providers can be tested independently; Domain remains framework-free | Task 3 | Agent-assisted, review diff | Not started
6 | 1. Document intelligence | 6 | Critical | Secure document ingestion: allowlisted file types, size/page limits, safe temporary storage, URI/SSRF prevention, malware hook and secrets validation. | Secure ingestion policy and validators | Unsafe URI/file inputs fail before OCR; non-test deployments reject dummy credentials | Task 4 | Review-driven | Not started
7 | 1. Document intelligence | 7 | High | Return field-level source, confidence and validation errors; support absent CRIB as an explicit state rather than a guessed value. | ExtractionResult DTOs | Low-confidence/missing fields route to manual review and never receive plausible defaults | Tasks 3,5 | Review-driven | Not started
8 | 1. Document intelligence | 8 | High | Improve salary, bank and CRIB parsing or use structured Azure fields; create a versioned ground-truth benchmark by document type. | Parser improvements and benchmark dataset | Every expected field has ground truth and traceable extraction result | Tasks 5,7 | Agent for tests; human reviews rules | Not started
9 | 1. Document intelligence | 9 | High | Run the benchmark and publish per-field/per-document precision, recall and exact-match results. | OCR evaluation report | Provisional gate: at least 90% exact field accuracy on versioned synthetic templates; real-document performance reported separately | Task 8 | Agent runs; human interprets | Not started
10 | 2. Deterministic vertical slice | 10 | Critical | Consolidate FinancialProfile/IncomeProfile into validated domain input value objects and replace object-typed engine contracts. | Validated typed domain contracts | Invalid units, ranges and required identifiers fail deterministically | Tasks 2,3 | Review-driven | Not started
11 | 2. Deterministic vertical slice | 11 | Critical | Correct application/applicant ID mapping and make generated timestamps come from TimeProvider. | Deterministic entity construction | Persisted and returned IDs/timestamps match the command and test clock | Task 10 | Agent-assisted | Not started
12 | 2. Deterministic vertical slice | 12 | Critical | Implement the approved affordability, income consistency, debt, employment, credit and penalty rules without undocumented proxies. | Final deterministic scoring engine | Worked rubric examples and every grade boundary pass | Tasks 2,10 | Review-driven | Not started
13 | 2. Deterministic vertical slice | 13 | High | Add specific explanations, recommended actions, manual-review reasons and D/E escalation intent. | Explainable assessment result | Every factor cites input and rule; C and D/E behavior is explicit | Task 12 | Review-driven | Not started
14 | 2. Deterministic vertical slice | 14 | Critical | Wire validator, in-memory repository, DI and POST /assess-feasibility; add handler/API tests and safe error mapping. | First usable API vertical slice | Valid synthetic documents return an assessment; malformed/unsafe inputs fail safely | Tasks 6,7,11,13 | Review-driven | Not started
15 | 3. Reproducible data and ML | 15 | High | Make synthetic generation reproducible with fixed seeds, version metadata, data dictionary and distribution checks. | Versioned synthetic dataset package | Same seed reproduces the same rows and class balance | Task 3 | Agent for glue code | Not started
16 | 3. Reproducible data and ML | 16 | Critical | Audit label leakage and define train/validation/test grouping; separate deterministic grade labels from historical approval outcomes. | Pre-registered split and label strategy | No direct target leakage; untouched test split is frozen | Task 15 | Human-owned methodology | Not started
17 | 3. Reproducible data and ML | 17 | Medium | Train A-E baseline models only as a research comparator to the deterministic engine. | Baseline classifier results | Accuracy, macro-F1, QWK and per-class recall reported on validation | Task 16 | Agent for code; human interprets | Not started
18 | 3. Reproducible data and ML | 18 | High | Train the distinct approval-probability baseline using outcome labels and leakage-safe features. | Approval baseline model | ROC-AUC, PR-AUC, Brier score and calibration curve produced | Task 16 | Agent for code; human interprets | Not started
19 | 3. Reproducible data and ML | 19 | High | Compare stronger models, tune only on validation, and calibrate probabilities where needed. | Model comparison table | Selection is based on pre-declared metrics, complexity and calibration | Tasks 17,18 | Review-driven | Not started
20 | 3. Reproducible data and ML | 20 | High | Evaluate subgroup performance, D/E recall, uncertainty and feature explanations; document synthetic-only validity limits. | Model card and fairness/error analysis | No production-validity claim is made from synthetic-only results | Task 19 | Human-owned analysis | Not started
21 | 3. Reproducible data and ML | 21 | High | Choose deterministic-only, ML-with-fallback, or ensemble strategy and package the model/runtime boundary. | Scoring strategy decision and versioned model | Decision is traceable to metrics and has deterministic fallback | Task 20 | Human decision; agent implements | Not started
22 | 4. RAG proposal optimizer | 22 | High | Define a de-identified historical case schema with financial summary, requested terms, decision, rationale, policy version and provenance. | HistoricalCase typed contract | No raw PII; approved and rejected outcomes are represented | Tasks 3,4,16 | Review-driven | Not started
23 | 4. RAG proposal optimizer | 23 | High | Build a synthetic/de-identified case corpus and labeled retrieval relevance set. | Versioned case corpus and relevance judgments | Each test query has expected relevant cases and provenance | Task 22 | Agent for data formatting | Not started
24 | 4. RAG proposal optimizer | 24 | High | Implement local embedding and cosine retrieval behind a typed interface; keep a file/in-memory index until scale justifies a vector database. | Historical case retrieval service | Top-K results include case ID, score and policy version | Task 23 | Agent-assisted, review diff | Not started
25 | 4. RAG proposal optimizer | 25 | High | Evaluate retrieval with Precision@K, Recall@K and qualitative error analysis. | Retrieval evaluation report | Metrics and failure examples are recorded before generation begins | Task 24 | Human reviews relevance | Not started
26 | 4. RAG proposal optimizer | 26 | Critical | Implement structured proposal generation grounded only in retrieved cases and approved constraints; defend against prompt injection in case text. | Typed LLM integration and prompt template | Output parses into a fixed schema and carries referenced case IDs | Tasks 4,24,25 | Review-driven | Not started
27 | 4. RAG proposal optimizer | 27 | Critical | Implement a policy constraint validator using verified rules, plus retry/repair, timeout, rate-limit and deterministic fallback behavior. | Constraint-first optimizer | Invalid terms never reach final output; three failed attempts end safely | Policy/legal confirmation; Task 26 | Human confirms rules | External gate
28 | 4. RAG proposal optimizer | 28 | High | Batch-evaluate grounding, constraint compliance, malformed output, latency, cost and human quality rubric. | Proposal evaluation report | 100% programmatic constraint compliance; all proposals cite grounding cases; limitations documented | Task 27 | Agent runs; humans rate | Not started
29 | 5. Persistence, API and UI | 29 | High | Design EF persistence entities and lease_feasibility schema for assessments, predictions, proposals and case metadata. | DbContext and migration design | No raw document contents stored by default; retention fields are explicit | Tasks 4,10,22 | Agent-assisted | Not started
30 | 5. Persistence, API and UI | 30 | High | Implement migrations, mappings and repositories with round-trip and database integration tests. | Working persistence layer | Migrations apply to dev DB and repository tests pass | Task 29 | Agent-assisted | Not started
31 | 5. Persistence, API and UI | 31 | Critical | Register Application/Infrastructure/Presentation, implement assess/predict/proposal controllers, Swagger contracts and consistent error responses. | Three API endpoints | All endpoints run through DI and appear in Swagger | Tasks 14,21,28,30 | Review-driven | Not started
32 | 5. Persistence, API and UI | 32 | Critical | Add authentication, role/ownership authorization, upload access controls and audit-safe request correlation. | Secured API boundary | Unauthorized cross-applicant access is denied and tested | Tasks 4,6,31 | Review-driven | Not started
33 | 5. Persistence, API and UI | 33 | High | Replace the Component 2 placeholder with document upload, extraction review, assessment, probability and proposal views. | Component 2 web workflow | Loading, empty, error, manual-review and traceability states are visible | Tasks 31,32 | Agent-assisted, visual review | Not started
34 | 5. Persistence, API and UI | 34 | High | Add API and browser end-to-end tests for the complete synthetic applicant journey. | End-to-end test suite | Upload to assessment to prediction to grounded proposal passes on a clean setup | Task 33 | Agent runs; human verifies UI | Not started
35 | 6. Integration and research closure | 35 | High | Define versioned integration contracts for land context and workflow handoff without direct module-domain references. | Decoupled integration DTOs/events | Architecture tests prevent cross-module coupling | Tasks 3,31 | Review-driven | Not started
36 | 6. Integration and research closure | 36 | Critical | Publish D/E escalation and write metadata-only audit records for assessments and proposals. | Escalation and audit flow | D/E emits once; A/B/C do not; no raw PII or document text enters audit logs | Tasks 13,32,35 | Review-driven | Not started
37 | 6. Integration and research closure | 37 | Critical | Run architecture, security and resilience tests: malformed files, extreme values, OCR outage, model failure, no similar cases and LLM outage. | Failure-mode test report | Every case fails safely with a clear action and no sensitive leakage | Tasks 6,21,27,32,36 | Agent runs; human triages | Not started
38 | 6. Integration and research closure | 38 | High | Run the untouched final evaluation for OCR, A-E scoring, approval model, retrieval and proposal quality. | Final accuracy and limitations report | All metrics use frozen data/splits and explicitly separate synthetic from real evidence | Tasks 9,20,25,28,37 | Human-owned analysis | Not started
39 | 6. Integration and research closure | 39 | High | Measure latency, throughput, model/LLM cost and demo fallback; rehearse a 3-5 minute end-to-end walkthrough. | Operational notes and demo recording/script | Demo works without external APIs using approved fallback data | Tasks 34,37 | Agent assists; human rehearses | Not started
40 | 6. Integration and research closure | 40 | Critical | Update architecture, implementation, methodology, results, ethics and limitation sections from actual evidence; obtain supervisor review. | Submission-ready evidence pack | No planned feature is described as implemented; supervisor decisions and pending gates are explicit | Tasks 38,39 | Human-owned writing | Not started

## Validation Matrix
Validation and research evidence matrix
Targets marked provisional must be confirmed with the supervisor before final evaluation. Synthetic performance must not be presented as real-world predictive validity.
Area | Metric or check | Current baseline | Gate | Evidence artifact | Decision rule
OCR extraction | Exact field accuracy by field and document type; confidence coverage | 76.0% (73/96) on 24 synthetic text documents | Provisional: >=90% on a versioned synthetic set; separately report real-document results if authorized | ocr-evaluation.md plus ground-truth dataset | Below gate: keep manual review and do not claim automated extraction readiness
Deterministic scoring | Boundary tests, worked examples, repeatability and explanation coverage | Engine exists; current WIP boundaries conflict with written rubric | 100% approved boundary/example tests; same input returns same score/explanation | scoring-decision.md and unit test output | Any contract mismatch blocks ML comparison and API release
A-E ML comparator | Macro-F1, quadratic weighted kappa and per-class recall | Not started | Report against deterministic baseline on frozen test split; no deployment gate from synthetic-only data | model-card-grade.md | Prefer simpler deterministic method unless ML adds reproducible value
Approval prediction | ROC-AUC, PR-AUC, Brier score and calibration curve | Not started | Thresholds pre-registered before final test; calibration acceptable for intended decisions | model-card-approval.md | Poor calibration blocks probability display to users
Fairness and uncertainty | Subgroup error rates, confidence/uncertainty and out-of-distribution behavior | Not started | Material disparities and unsupported populations are documented and routed to manual review | fairness-error-analysis.md | Unexplained disparity blocks automated recommendation use
RAG retrieval | Precision@K, Recall@K and relevance error review | Not started | Evaluated on labeled queries; returned cases include provenance and policy version | retrieval-evaluation.md | Poor retrieval blocks proposal generation
Proposal generation | Constraint compliance, grounding coverage, parse failures and human rubric | Not started | 100% programmatic constraint compliance; 100% case citations; parse failures fail safely | proposal-evaluation.md | Any invalid final term blocks release
Security and privacy | AuthZ tests, upload validation, PII log scan, secrets and retention controls | Masked logger exists; no full control path | No cross-applicant access; no raw PII/document text in logs; unsafe files rejected | threat-model.md and security test output | Any sensitive-data leak is release-blocking
API workflow | Assess, predict and generate endpoints plus negative cases | No Component 2 endpoints | All endpoints pass integration tests and consistent error mapping | API test report and Swagger export | Any stub/NotImplementedException blocks UI integration
End-to-end workflow | Synthetic applicant from upload through grounded proposal and escalation | UI placeholder | Clean-environment E2E passes; C and D/E review/escalation paths are visible | E2E output and demo script | Broken visible workflow blocks demo readiness
Operational resilience | Latency, timeout, retry, external outage and fallback behavior | Not measured | Fallback demo works without live OCR/LLM; costs and limits documented | operational-notes.md | No fallback blocks live demo readiness

## Antigravity Prompts
Antigravity execution prompts
Use one prompt at a time after its prerequisite gate passes. Keep GovernanceIntelligence and LandIntelligence read-only references unless a separately approved integration task requires a contract change.
Prompt | Use after | Paste into Antigravity | Required proof before moving on
P0 - Baseline | Now | Work only in Component 2 and its tests/docs. First inspect git status and preserve the existing uncommitted scoring-engine edit and untracked scoring tests. Run the Component 2 unit test project and API build, record exact results, and propose a minimal sequence for reconciling the scoring contract. Do not edit code until you have listed the rubric/code/test mismatches. | Diff review, git status unchanged except intended files, test and build output
P1 - Scoring contract | Supervisor has chosen the A-E bands and weights | Update the Component 2 rubric, typed inputs and deterministic scoring engine so one approved contract defines all thresholds, weights, units and actions. Remove savings-as-lease-cost and 5%-of-total-debt assumptions unless they are explicitly approved. Fix application/applicant ID and TimeProvider handling. Add worked-example and boundary tests. Do not touch ML or RAG. | Approved rubric, focused diff, boundary/example tests, all 44+ Component 2 tests green
P2 - OCR hardening | Typed document/input contract is stable | Refactor Component 2 OCR into a provider boundary and document-specific extractors. Add file/URI validation, field confidence, source evidence, optional CRIB handling and explicit manual-review errors. Improve the versioned synthetic benchmark from the current 73/96 field baseline. Never log raw document text or PII. Run unit tests and the batch benchmark. | Per-document metrics, failure examples, security tests, no raw PII logs
P3 - Assess vertical slice | P1 and P2 pass | Complete only POST /assess-feasibility: invoke the validator, map extracted evidence to validated domain inputs, score, persist to an in-memory repository, return explanations/manual-review state, register DI and add controller/API tests. Keep the future ML and RAG handlers untouched. Match existing controller error conventions without referencing another module's Domain assembly. | Running endpoint, Swagger contract, positive and negative API tests
P4 - Reproducible dataset | Feature and label definitions are frozen | Create a deterministic synthetic-data pipeline with a fixed seed, version metadata, data dictionary and class/distribution report. Separate A-E grade labels from historical approval outcomes and audit target leakage. Create frozen train/validation/test splits. Do not train models until the split and label report is reviewed. | Reproducible hashes/counts, label/split report, no target leakage
P5 - ML evaluation | P4 reviewed | Train an A-E research comparator and a separate approval-probability model. Report macro-F1, QWK and per-class recall for grades; ROC-AUC, PR-AUC, Brier score and calibration for approval. Compare simple and stronger models without touching the frozen test split. Document synthetic-only validity limits, subgroup errors and the deterministic fallback. Package only the selected model. | Model cards, comparison table, frozen-test discipline, versioned artifact
P6 - RAG retrieval | Historical case schema and approved/de-identified corpus exist | Implement a typed historical-case corpus, local embeddings and cosine Top-K retrieval in Component 2. Return case IDs, similarity scores, provenance and policy version. Create labeled queries and evaluate Precision@K/Recall@K before adding an LLM. Keep the index file/in-memory unless measured scale requires a vector database. | Retrieval metrics, relevant/irrelevant examples, architecture isolation tests
P7 - Proposal optimizer | P6 passes and policy constraints are verified | Implement structured proposal generation grounded only in retrieved cases and verified constraints. Add prompt-injection resistance, schema parsing, constraint validation, repair attempts, timeout/rate-limit handling and deterministic fallback. Every proposal must cite source case IDs. Add malformed-output and invalid-term tests and a batch evaluation. | 100% constraint compliance, citations, safe failure tests, latency/cost notes
P8 - Persistence and API | Domain, ML and RAG contracts are stable | Add Component 2 EF persistence entities, mappings, DbContext, migration and repositories in a lease_feasibility schema. Register Application/Infrastructure/Presentation and implement assess, predict and generate endpoints with Swagger, authentication, ownership authorization and metadata-only audit correlation. Add database and API integration tests. | Migration proof, repository tests, secured endpoint tests, Swagger
P9 - UI and final integration | P8 passes | Replace the Component 2 placeholder with the complete synthetic applicant workflow: upload, extraction review, assessment factors, approval probability, grounded proposal, manual-review and error states. Add browser E2E coverage. Then publish D/E escalation through a decoupled integration event and add metadata-only audit records. Preserve module isolation. | Visible browser flow, E2E test, event tests, no cross-module Domain reference
P10 - Final evidence | All implementation phases pass | Run the frozen final evaluations and failure-mode suite. Produce an evidence pack for OCR, scoring, approval model, retrieval, proposal quality, security, latency/cost and demo fallback. Update report text from actual results only; label synthetic evidence and pending real-data/ethics validation honestly. | Final reports, clean rerun commands, demo script/recording, supervisor review notes

## Risks and Decisions
Risks, decisions and external gates
Resolve critical decisions before the dependent implementation phase. Do not convert pending assumptions into code constants or research claims.
Risk or decision | Current evidence | Impact | Treatment | Owner or authority | Gate
A-E rubric conflict | Document: 85/70/50/30 with one weight set; engine/tests: 80/60/40/20 with another | Invalidates comparisons and user meaning | Approve one version and make docs, code, examples and tests identical | Student + supervisor/domain adviser | Before Phase 2
Affordability input missing | Engine substitutes SavingsToIncomeRatio for income-to-lease-cost | Score does not measure the stated factor | Add requested rent/payment/deposit and defined affordability ratio | Student + domain adviser | Before Phase 2
Debt semantics unclear | Engine assumes 5% of ActiveLoanObligations is monthly payment | Material score distortion | Store monthly obligation explicitly or document a verified conversion | Student + finance/domain adviser | Before Phase 2
CRIB optionality | TAF says optional; command requires a CRIB URI | Excludes valid applicants and encourages fabricated defaults | Model missing CRIB as an explicit state and route uncertainty to review | Supervisor/domain adviser | Before OCR/API release
Synthetic-data optimism | Generator samples grade/outcome and then creates correlated features | Metrics can measure the generator rather than real generalization | Leakage audit, frozen splits, data card and explicit synthetic-only claims | Student + supervisor | Before ML
Real data and ethics | No verified approval or historical dataset in the branch | Privacy/legal/research risk | Use synthetic/de-identified data until written access and clearance exist | University and data owner | External gate
OCR reliability | 76.0% exact fields on synthetic text files | Wrong financial inputs produce wrong decisions | Confidence, review state, benchmark improvements and real-doc validation if authorized | Student | Before assess endpoint is demo-ready
Cloud OCR residency | Azure provider selected; no approved residency/retention decision | Financial documents may leave approved boundary | Confirm region/contract; keep provider swappable; encrypt and minimize retention | Data owner + supervisor | Before real data
Unsafe document URI | Service accepts HTTP/local paths and can read local files | SSRF, unauthorized file access and denial-of-service | Controlled upload storage, allowlists, limits and no arbitrary user-supplied server path | Student | Before API exposure
Hard-coded income consistency | Assessment handler sets 0.85 for all applicants | Misleading score and research result | Derive from statement period or mark missing/manual review | Student | Before Phase 2
Identity and time defects | Engine persists ApplicantId as ApplicationId and ignores evaluationTimestamp | Audit trail cannot be trusted | Pass both IDs explicitly and construct entities with TimeProvider output | Student | Before persistence
No API authorization | Component 2 is not registered and no policy exists | Financial data exposure | Add authenticated ownership/role checks with negative tests | Student + team | Before UI/API integration
Unverified policy constants | Old plan proposes copying limits from another component | Could encode incorrect law/policy and couples modules | Use approved sources/configuration and version the applicable policy | Domain/legal adviser | Before proposal validator
LLM hallucination and injection | No generator exists yet | Unsafe or fabricated proposal terms | Retrieved-content sanitization, structured output, programmatic validator, citations and human approval | Student | Before proposal release
Branch integration risk | Local branch is far ahead of remote Component 2 and has dirty WIP | Harder review/merge and accidental loss | Checkpoint Component 2 work separately, rebase/merge only after tests and team coordination | Student + team | Before broad implementation

## Source Traceability
Source traceability
The plan distinguishes document requirements from code evidence and runtime verification. Local absolute paths are intentionally omitted.
Source | Location | Used for | Verified finding | Limitation
Topic Assessment Form v2.2 | TAF.pdf, page 4 | Component 2 solution scope | OCR/data extraction, A-E eligibility, approval prediction, historical cases, RAG and proposal generation | TAF gives categories, not numeric scoring thresholds or implementation architecture
Topic Assessment Form v2.2 | TAF.pdf, page 7 | Data and ethics assumptions | Synthetic data is allowed when real data is unavailable; privacy and ethical clearance are required | Institutional access is described as possible, not verified
Topic Assessment Form v2.2 | TAF.pdf, page 9 | Member objective and task list | Eight Component 2 tasks and novelty statement belong to IT23182950 | No acceptance metrics are specified
Existing plan workbook | Overview, Day-by-Day Plan, Antigravity Prompts and Notes | Original 90-day breakdown and agent workflow | Useful dependency ordering and prompts | All day statuses remain Not Started and no longer match the branch
Git branch | Component_02_RH | Actual implementation state | Latest committed Component 2 work includes deterministic scoring; working tree contains further scoring/test changes | Branch is also ahead with unrelated merged component work
Component 2 source | src/Modules/LeaseFeasibility | Domain, application, infrastructure and presentation status | Domain/app/OCR scaffold exists; prediction/proposal handlers are stubs; persistence/controller folders are empty | Static inspection does not prove deployed behavior
Component 2 web source | StateLandGovernance.Web/src/app/component-02/page.tsx | UI status | Coming-soon placeholder only | No browser runtime was required to establish absence of workflow
Runtime verification | dotnet test Component 2 unit test project | Current unit baseline | 44 passed, 0 failed | Includes mocks and uncommitted boundary tests; not an integration or real-data result
Runtime verification | dotnet build StateLandGovernance.Api.csproj | Solution integration baseline | Build passed with 0 warnings and 0 errors | Build success does not mean Component 2 is registered or callable
Runtime verification | OcrBatchTester | Extraction baseline | 73/96 fields correct across 24 synthetic text documents (76.0%) | Synthetic text fixtures do not represent scanned real-world documents